## Sheet1
PO Number | PO Line | PO Status | Item Number | Description | Vendor Item | Safran Due Date | Vendor Due Date | Qty Ordered | Unit of Measure | Qty Received | Qty Rejected | Drawing Number | Last Reception Date | Promise Date
SNZR000189 | 1 | Ordered | 156-111-420-6SP | LOCK for seal 4 | - | Dec 14 2025 | Dec 5 2025 | 1000 | EA | 0 | 0
SNZR000189 | 2 | Planned | 156-111-420-6SP | LOCK for seal 4 | - | Jun 5 2026 | May 27 2026 | 1000 | EA | 0 | 0
SNZR000189 | 3 | Planned | 156-111-420-6SP | LOCK for seal 4 | - | Feb 4 2027 | Jan 26 2027 | 1000 | EA | 0 | 0
SNZR000200 | 1 | Planned | 056-000-420-6SP | LOCK for seal 4 | - | Oct 8 2027 | Sep 29 2027 | 1000 | EA | 0 | 0
SNZR000183 | 2 | Ordered | 305-056-201-0SP | Turbine shaft bushing | - | Jun 8 2025 | Jun 1 2025 | 3000 | EA | 2917 | 0 |  | Oct 16 2025
SNZR000194 | 1 | Ordered | 315-265-208-0SP | Turbine shaft bushing | - | Oct 8 2025 | Oct 1 2025 | 3000 | EA | 0 | 0
SNZR000198 | 1 | Planned | 315-265-208-0SP | Turbine shaft bushing | - | Jan 15 2026 | Jan 8 2026 | 3000 | EA | 0 | 0
SNZR000198 | 2 | Planned | 315-265-208-0SP | Turbine shaft bushing | - | Apr 15 2026 | Apr 8 2026 | 3000 | EA | 0 | 0
SNZR000198 | 3 | Planned | 315-265-208-0SP | Turbine shaft bushing | - | Aug 15 2026 | Aug 8 2026 | 3000 | EA | 0 | 0
SNZR000198 | 4 | Planned | 315-265-208-0SP | Turbine shaft bushing | - | Jan 15 2027 | Jan 8 2027 | 3000 | EA | 0 | 0